## Timeline
Milestone | Category (FF&E / OS&E / Both) | Description | Target Start (relative to opening) | Target End (relative to opening) | Primary Owner | Dependencies | Status | Notes
Finalize design intent & room mock-up | Both | Mock-up sign-off unlocks shop drawings and finish masters | T-12 months | T-9 months | Developer + Design + Operator |  | Not Started
RFQ + supplier shortlist (FF&E) | FF&E | Vet capacity; gather sample plans and compliance evidence | T-10 months | T-8 months | Procurement/FF&E lead | Finalize design intent & room mock-up | Not Started
Golden samples & finish masters approved | Both | Lock specs, compliance marks, labeling, packaging | T-9 months | T-7 months | Developer/Brand + Procurement | RFQ + supplier shortlist (FF&E) | Not Started
Place FF&E POs; production scheduling | FF&E | Dual-source critical items; embed QC gates | T-8 months | T-6 months | Procurement + Factory | Golden samples & finish masters approved | Not Started
OS&E spec finalization & RFQ | OS&E | Confirm par levels by key count and opening wave | T-6 months | T-4 months | Procurement/OS&E lead + Operator | Finalize design intent & room mock-up | Not Started
Pre-production inspections (FF&E) | FF&E | Materials/components check vs. golden samples | T-6 months | T-5 months | QC lead | Place FF&E POs; production scheduling | Not Started
During-production checks (FF&E) | FF&E | Catch systemic issues at 20–50% completion | T-5 months | T-3 months | QC lead | Pre-production inspections (FF&E) | Not Started
FF&E consolidation & bookings (ocean) | FF&E | Favor FCL where feasible; firm sailings | T-3 months | T-2 months | Logistics | During-production checks (FF&E) | Not Started
Pre-shipment inspections (FF&E/OS&E) | Both | AQL sampling; packaging, labeling, documents | T-2 months | T-1 month | QC lead | FF&E consolidation & bookings (ocean); OS&E production | Not Started
OS&E production + partial air for stragglers | OS&E | Only if justified by schedule risk | T-2 months | T-1 month | Procurement + Logistics | OS&E spec finalization & RFQ | Not Started
Ocean arrival, customs, deconsolidation | Both | Final-mile plans tied to install phases | T-1 month | T-2 weeks | Logistics + Broker | FF&E consolidation & bookings (ocean); Pre-shipment inspections | Not Started
Site installation (FF&E), then OS&E room-setup | Both | Room-by-room sign-off; damage/claims process | T-2 weeks | T-0 | Site PM + Installer + Ops | Ocean arrival, customs, deconsolidation | Not Started

## FF&E_OS&E_Checklist
Phase | Checklist Item | Category (FF&E / OS&E / Both) | Details | Responsible | Target Timing (relative to opening) | Status | Notes
Design & Mock-up | Confirm brand standards and design brief | Both | Ensure operator, brand, and developer alignment on look/feel and functional requirements | Developer + Operator + Designer | T-12 to T-10 months | Not Started
Design & Mock-up | Build and review room mock-up | Both | Validate room layout, clearances, ergonomics, and guest experience | Developer + Designer | T-12 to T-9 months | Not Started
Design & Mock-up | Freeze FF&E and OS&E scope per room type | Both | Define item lists by room/zone including back-of-house | Procurement + Ops | T-11 to T-9 months | Not Started
RFQ & Supplier Selection | Issue RFQs to pre-vetted suppliers | FF&E | Send complete specs, drawings, and quantities with quality and compliance requirements | Procurement/FF&E lead | T-10 to T-8 months | Not Started
RFQ & Supplier Selection | Evaluate quotes and capacity | FF&E | Compare pricing, lead times, capacity, compliance history, and quality performance | Procurement + Finance | T-9 to T-8 months | Not Started
RFQ & Supplier Selection | Confirm OS&E supplier shortlist | OS&E | Select suppliers for linens, tableware, housekeeping equipment, and small appliances | Procurement/OS&E lead | T-6 to T-4 months | Not Started
Samples & Compliance | Request golden samples for key FF&E items | FF&E | Casegoods, seating, decorative lighting, and custom textiles | Procurement + QC | T-9 to T-7 months | Not Started
Samples & Compliance | Approve finishes and color standards | Both | Sign off physical samples and set tolerance ranges (e.g., delta-E) | Developer/Brand + QC | T-9 to T-7 months | Not Started
Samples & Compliance | Confirm fire, electrical, and safety standards | Both | List applicable standards by market (e.g., TB117-2013, UL, CE) and test requirements | Procurement + QC | T-9 to T-7 months | Not Started
Production & QC | Lock production schedule with suppliers | Both | Confirm line booking, monthly output, and shipment plan by batch | Procurement + Factory | T-8 to T-6 months | Not Started
Production & QC | Conduct pre-production inspection (PPI) | FF&E | Check materials/components, workmanship samples, and compliance plan | QC lead | T-6 to T-5 months | Not Started
Production & QC | Conduct during-production inspection (DPI) | FF&E | Inspect 20–50% of output to catch systemic issues early | QC lead | T-5 to T-3 months | Not Started
Production & QC | Conduct pre-shipment inspection (PSI) | Both | Apply AQL sampling; verify packaging, labeling, and documentation | QC lead | T-2 to T-1 month | Not Started
Logistics & Customs | Confirm packing lists and HS codes | Both | Align item descriptions, HS codes, and declared values with broker | Logistics + Broker | T-2 to T-1 month | Not Started
Logistics & Customs | Book ocean freight and consolidation plan | FF&E | Plan FCL/LCL mix, sailing windows, and destination handling | Logistics | T-3 to T-2 months | Not Started
Logistics & Customs | Plan air shipments for critical items (if needed) | Both | Define criteria and budget for air freight exceptions | Procurement + Logistics | T-2 to T-1 month | Not Started
Site Installation & Handover | Coordinate site readiness and room handover | Both | Align with GC/site PM on clean floors, lifts, and storage zones | Developer + Site PM | T-1 month to T-2 weeks | Not Started
Site Installation & Handover | Implement FF&E installation schedule | FF&E | Room-by-room installation with snagging and damage reporting | Site PM + Installer | T-2 weeks to T-0 | Not Started
Site Installation & Handover | Stock OS&E in guest rooms and back-of-house | OS&E | Par levels by room/department with labeling and storage standards | Ops + Housekeeping | T-2 weeks to T-0 | Not Started
Site Installation & Handover | Run final walk-through and punch list | Both | Multi-party inspection (developer, operator, brand) before soft opening | Developer + Operator | T-1 week to T-0 | Not Started